## Part 1 Plan
Task | Time Estimate | Start Date | Due Date | Time it took to complete | Status | Done | Notes such as what came up and how you had to adjust your schedule or if you hit your due date.
Create a sepperate method for URL and change is signature | 0.5 Hours | 2023-04-14 | 2023-04-17 | 0.5 Hours | Completed | TRUE | Cannot pass whole organization
Fix email incorrect loop and update it | 0.5 hours | 2023-04-14 | 2023-04-17 | 0.5 hours | Completed | TRUE
Create a sepperate method for double validation | 1-2 hours | 2023-04-14 | 2023-04-17 | 1 hour | Completed | TRUE | Cannot include Q
Create a sepperate method for inserting end of line characters | 0.5 hours | 2023-04-14 | 2023-04-17 | 0.25 hours | Completed | TRUE
Fix incorrect email and password and add one extra attempt. and write reciept to a file | 1 hour | 2023-04-14 | 2023-04-17 | 0.5 hours | Completed | TRUE
Brainstrom new features and methods I need to implement and make a list | 1-2 hours | 2023-04-16 | 2023-04-16 | 1 hour | Completed | TRUE
Clean up all messy code | 1 hour | 2023-04-17 | 2023-04-18 | 3 hours | Completed | TRUE
Create a method to search for the desired organization | 1 hour | 2023-04-17 | 2023-04-18 | 1 hour | Completed | TRUE
Create a method to create organizatins and store them into a file | 1-2 hours | 2023-04-17 | 2023-04-18 | 2 hours | Completed | TRUE | Include Nodes and linked lists
Update the password in organization and implement a new feature | 0.5 hours | 2023-04-18 | 2023-04-18 | 0.5 hours | Completed | TRUE
Create an organization reciept method | 0.5 hours | 2023-04-18 | 2023-04-18 | 1 hour | Completed | TRUE
Update donation reciept to add to the file in previous method | 0.5 hours | 2023-04-18 | 2023-04-19 | 0.5 hours | Completed | TRUE
At the end of the method, deallocate all memory from organizatiions | 0.25 hours | 2023-04-19 | 2023-04-19 | 0.25 hours | Completed | TRUE
Create a method to organize the list alphabetically | 1 hour | 2023-04-20 | 2023-04-20 | 2 hours | Completed | TRUE
Create a table of inputs to test | 1-0.5 hours | 2023-04-20 | 2023-04-20 | 1 hour | Completed | TRUE
Run Test Cases and Debug | 2 hours | 2023-04-20 | 2023-04-20 | 4 hours | Completed | TRUE