## Project Plan Template
Project Planning Spreadsheet
| PROJECT TITLE |  | START DATE
| Fundrasing Website |  | 2023-03-12 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| Carson King |  | 2023-04-05 |  |  | 25
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
3 | Project Writing and Implementing | Complete |  | 2023-03-12 | 2023-04-05 | 25
3.1 | Constants and Prototypes | Complete |  | 2023-03-18 | 2023-03-18 | 1
3.2 | All methods for part 1 | Complete |  | 2023-04-01 | 2023-04-03 | 3
3.2.1 | All methods for part 2 | Complete |  | 2023-04-04 | 2023-04-05 | 2
3.2.2 | All methods for part 3 | Complete |  | 2023-04-04 | 2023-04-05 | 2
3.3 | Add calls and set up main | Complete |  | 2023-04-01 | 2023-04-05 | 5
3.3.1 | Debugging | Complete |  | 2023-04-01 | 2023-04-05 | 5
4 | Tests Cases and Reflections | Complete |  | 2023-04-01 | 2023-04-05 | 5
4.1 | Tested for part 1 | Complete |  | 2023-04-01 | 2023-04-05 | 5
4.2 | Tested for part 2 | Complete |  | 2023-04-04 | 2023-04-05 | 2
4.3 | Tested for Part 3 | Complete |  | 2023-04-04 | 2023-04-05 | 2
4.4 | Reflection questions | Complete |  | 2023-04-05 | 2023-04-05 | 1

## BLANK - Project Plan Template
PROJECT PLAN TEMPLATE
| PROJECT TITLE |  | START DATE
PROJECT DURATION
| PROJECT MANAGER |  |  |  |  | in days
1
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT CONCEPTION AND INITIATION |  |  |  |  | 1 |  | Not Started
1.1 | – Project Charter |  |  |  |  | 1 |  | In Progress
1.1.1 | –– Project Charter Revisions |  |  |  |  | 1 |  | Complete
1.2 | – Research |  |  |  |  | 1 |  | On Hold
1.3 | – Projections |  |  |  |  | 1
1.4 | – Stakeholders |  |  |  |  | 1
1.5 | – Guidelines |  |  |  |  | 1
1.6 | – Project Initiation |  |  |  |  | 1
2 | PROJECT DEFINITION AND PLANNING |  |  |  |  | 1
2.1 | – Scope & Goal Setting |  |  |  |  | 1
2.2 | – Budget |  |  |  |  | 1
2.3 | – Communication Plan |  |  |  |  | 1
2.4 | – Risk Management |  |  |  |  | 1
3 | PROJECT LAUNCH & EXECUTION |  |  |  |  | 1
3.1 | – Status & Tracking |  |  |  |  | 1
3.2 | – KPIs |  |  |  |  | 1
3.2.1 | –– Monitoring |  |  |  |  | 1
3.2.2 | –– Forecasts |  |  |  |  | 1
3.3 | – Project Updates |  |  |  |  | 1
3.3.1 | –– Chart Updates |  |  |  |  | 1
4 | PROJECT PERFORMANCE / MONITORING |  |  |  |  | 1
4.1 | – Project Objectives |  |  |  |  | 1
4.2 | – Quality Deliverables |  |  |  |  | 1
4.3 | – Effort & Cost Tracking |  |  |  |  | 1
4.4 | – Project Performance |  |  |  |  | 1
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.